## Sheet1
Task ID | Task Name | Assigned Team Member | Deadline | Completed
1 | Complete Weekly Documentation Requirements | Timothy Finn | 2018-09-08 | Yes
2 | Research tools needed to complete project | Yeqing Liu | 2018-09-08 | Yes
3 | Complete Project plan | Josh Francis | 2018-09-08 | Yes
4 | Research RaspberryPi and ideas associated to completing project | Michael Douglas | 2018-09-08 | Yes
5 | Research LED power requirements and setup. | George Proios | 2018-09-08 | Yes
6 | Complete Gantt Chart, Review Documentation | Timothy Finn | 16/8/2018 | Yes
7 | Develop Code to hold JSON format | Yeqing Liu | 16/8/2018 | Yes
8 | Investigate and plan solder work on LED strips | Josh Francis | 16/8/2018 | Yes
9 | Check Supplied Raspberry pi and workout plan for integrating into project | Michael Douglas | 16/8/2018 | Yes
10 | Investigate Power and LED strip requirements | George Proios | 16/8/2018 | Yes
11 | Look into appropriate libraries for driving LED's | Josh Francis | 16/8/2018 | Yes
12 | Construct simple circuit with provided materials for proof of concept | Josh Francis | 16/8/2018 | Yes
13 | Create draft Issues Document | Timothy Finn | 16/8/2018 | Yes
14 | Create Github Repo relocate Documentation, Work on code implementations | Timothy Finn | 2018-08-23 | Yes
15 | Work on LED implementation | Josh Francis | 2018-08-23 | Yes
16 | Work on RasberryPi implementation | Michael Douglas | 2018-08-23 | Yes
17 | Liase with Stakeholder, review code received | George Proios | 2018-08-23 | Yes
18 | create JSON interface | Yeqing Liu | 2018-08-23 | Yes
19 | Complete Documentation updates, Upload To gitHub | Timothy Finn | 2018-08-30 | Yes
20 | Work on Widows Implementation | Yeqing Liu | 2018-08-30 | Yes
21 | Printing replica 3D Brain | George Proios | 2018-08-30 | Yes
22 | Focusing on LED strip driver implementation | Josh Francis | 2018-08-30 | Yes
23 | Focusing on implementing Rasbperry PI | Michael Douglas | 2018-08-30 | Yes
24 | Work on Documenation, Complete BSL induction | Timothy Finn | 2018-09-06 | Yes
25 | Work on Java implementation, Complete BSL induction | Yeqing Liu | 2018-09-06 | Yes
26 | Work on LED implementation, Complete BSL induction | Josh Francis | 2018-09-06 | Yes
27 | Work on Raspberry Pi interface, Complete BSL induction | Michael Douglas | 2018-09-06 | Yes
28 | Work on brain diagram, Complete BSL induction | George Proios | 2018-09-06 | Yes
29 | Discuss and Implment Presentation Poster | George Proios | 2018-09-13 | Yes
30 | Work on Documentation | Timothy Finn | 2018-09-13 | Yes
31 | Test Brain activity visual representation | Josh Francis | 2018-09-13 | Yes
32 | Test Raspberry pi implementation. | Michael Douglas | 2018-09-13 | Yes
33 | Code Refactoring | Yeqing Liu | 2018-09-13 | Yes
34 | Code Refactoring | Yeqing Liu | 2018-09-20
35 | Work on Documentation | Timothy Finn | 2018-09-20
36 | Work on Design of Poster | George Proios | 2018-09-20
37 | workd on LED and heat map implementation | Josh Francis | 2018-09-20
38 | Work on integrating LED drivers with Raspberry PI | Michael Douglas | 2018-09-20